## Sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Create project website | bar: Week 1
Create Git Repository | bar: Week 1
Create tenative Gantt Chart | bar: Week 1
Find apropriate peripheral libraries | bar: Week 1 to Week 2
Make a general GUI space | bar: Week 1 to Week 3
Develop general file system i.e Save, import, export | bar: Week 3 to Week 4
Develop MIDI enviornemnt | bar: Week 4 to Week 8
Develop peripheral functions | bar: Week 9 to Week 11
Testing | bar: Week 12 to Week 13
Final Presentation | bar: Week 14